## Summary
Test Case Summary
Project Name - | Daraz
Module Name - | Signup |  |  |  |  | Status | Total No. | Result :
Test Case Version | 1.0.0 |  |  |  |  | PASS | 97
Written By | Al Faysal Bin Asad |  |  |  |  | FAIL | 7
Executed By | [5 empty] | Not Executed | 0 | New Features | Testing Scope | Testing Environment :
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | Out of Scope | 0 |  |  | Test Environment
TEST EXECUTION SUMMARY | [5 empty] | Sub Total | 104
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 97 | 7 | 0 | 0 | 104
Grand Total | 97 | 7 | 0 | 0 | 104
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Sign Up_Log In_Daraz
TEST CASE SUMMARY
[10 empty] | PASS | 97
Product Name |  | Daraz | TC Start Date | 15/9/2022 | TC Execution Start Date | 15/9/2022 |  |  |  | FAIL | 7
Module Name |  | Sign Up, Sign in | TC End Date | 21/09/2022 | TC Execution End Date | 21/09/2022 |  |  |  | Not Executed | 0
|  |  | Test Case Developed By | Al Faysal Bin Asad | Browser (tested) | Yes |  |  |  | Out of Scope | 0
Developer Name (TL) |  | Mr. John | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  | TOTAL | 104
Module | Type of Testing | Features | Test Case ID | Test Cases | Expected Result | Actual Result | Test Data | Test Step Description/Reproducing Steps | Actual Result | Bug Screen Shot | Status | Remarks
User Management
User Management | Functional Testing | Sign Up | TC_0001 | Try to sign up by entering nothing. | A validation message will be shown for trying to sign up by entering nothing in input field. | It shows a validation message as expected. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'SIGN UP' | Language could be changed to English/Chinese as per preference. | Blank_Sign Up | Passed |  | Improvement Suggestions
|  |  | TC_0002 | Asterisk sign for mandatory fields | Mandatory fields should be marked with asterisks sign. | Found as expected. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'SIGN UP' |  | Asterisk | Passed
|  |  | TC_0003 | Blank 'Password' field. | If any input is given in 'Full Name' field and all the data is erased then it will show a validation message. | It shows a validation message as expected. | asdfgh, N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a name in 'Full Name' field then erase it |  | Blank_Password | Passed |  | SL No. | Module | Feature Name | Test Data | Improvement | Reproducing Steps | Screenshots
[13 empty] | 1 | User Management | Sign Up | 12345678912345600 | A validation message should be shown in the 'Phone Number' field for the digit limit of phone number. | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Sign up with Mobile' | Phone no. limit
|  |  | TC_0004 | Sign Up option change using Phone Number or Email. | Sign up option will be changed to using mobile number after clicking on 'Sign Up with Mobile' button. | It changed according to the expected result. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Mobile' button |  | Sign Up_Mobile | Passed |  | 2 |  |  | N/A | To make a strong password symbol/special character can be me made mandatory and also can be shown in hints | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter valid mail address 6) Enter email verification code 7) Enter a password without special character. | Password Suggestion
|  |  | TC_0005 |  | Sign up option will be changed to using Email after clicking on 'Sign Up with Email' button. | It changed according to the expected result. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button |  | Sign Up option | Passed |  | 3 |  |  | N/A | Capitalization' should be maintained properly in 'Sign Up' page. | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' | Capitilaztion
[13 empty] | 4 |  | Login | N/A | To reset password using email, in 'Email Verification' page, mouse icon should be changed for hovering over 'Send' hyperlink. | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button. | Masked Email
|  |  | TC_0006 | Blank 'Email Address' field | Validation message will be shown for keeping 'Email Address' field blank. | Result shows as expected. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter an email address in 'Email Address' field then erase it. |  | Empty Mail | Passed
|  |  | TC_0007 | Space before email address | Validation message for space before email address. | Result shows as expected. | _faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter an email address in 'Email Address' field using a space before email address. |  | Space before email | Passed
|  |  | TC_0008 | Space after email address | Validation message for space after email address. | Result shows as expected. | faysalbinasad3334@gmail.com_ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter an email address in 'Email Address' field using a space after email address. |  | Space after mail | Passed
|  |  | TC_0009 | Valid Email format checking | A valid email address should be accepted by the system. | Email address was accepted by the system as per the expectations. | faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the test data in 'Email Address' field. |  | Valid Email | Passed
|  |  | TC_0010 | Email with semicolon or comma. | Email Address' field shouldn't allow any comma or semicolon | Result was as per expectations. | faysalbinasad3334;com@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the test data in 'Email Address' field. |  | Email with SC | Passed
|  |  | TC_0011 | Email Address' field clear | By clicking on a cross button 'Email Address' field will be cleared. | Email Address' field was cleared as per the expectations. | faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the test data in 'Email Address' field 6) Click on the cross icon to clear 'Email Address' field. |  | Clear Email | Passed
|  |  | TC_0012 | Check whether the slide button is working or not to get 'Email Code' | After sliding the button to get email verification code, it will show a text box named 'SMS Verification Code'. | Slide button works as per expectations. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter valid mail address 6) Slide the button 'Slide to get Email Code'. |  | Slide Button | Passed
|  |  | TC_0013 | Timer checking for resending the verification code. | After sliding the button to get email verification code, it will show a text box named 'SMS Verification Code' and a timer will be counted for 60 seconds to resend the code. | A timer was found as per the expected result. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter valid mail address 6) Slide the button 'Slide to get Email Code'. |  | Timer | Passed
|  |  | TC_0014 | Resend button checking for resending email verification code | A verification code will be sent after clicking on 'Resend' button in the 'Email Verification Code' field. | Resend' button worked as per expectations and a new code was sent to the mail. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter valid mail address 6) Slide the button 'Slide to get Email Code' 7) Click on the 'Resend' button. |  | Resend 1 | Passed
Resend 2
|  |  | TC_0015 | Message for containing password hints | When 'Password' field is blank it will show a hints to form a password | Password hints was shown as per the expectations | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter valid mail address 6) Enter email verification code 7) Keep Password field blank. |  | Message for Pass Int | Passed
|  |  | TC_0016 | Maximum length checking of password with valid email | A validation message will be shown for exceeding maximum length of the password. | Validation message was shown as per expected result. | a123456789123456789123456789123456781234567891234566666666 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter valid mail address 6) Enter email verification code 7) Enter password with more than 50 characters. |  | Max Validation 1 | Passed
|  |  | TC_0017 | Minimum length checking of password with valid email | A validation message will be shown for not fulfilling minimum length of the password. | Validation message was shown as per expected result. | fay | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter valid mail address 6) Enter email verification code 7) Enter password with more than 6 characters. |  | Min Pass Email | Passed
|  |  | TC_0018 | Password' field clear | By clicking on a cross button 'Password' field will be cleared. | Password' field was cleared as per the expectations. | 123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the email address in 'Email Address' field 6) Enter the password in 'Password' field 7) Click on the cross icon to clear 'Password' field. |  | Clear Email | Passed
|  |  | TC_0019 | Red border for blank field | A red border will be shown marking the blank field as blank. | A red border was as per the expected result. | Blank Password field | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the email address in 'Email Address' field 6) Enter nothing in 'Password' field. |  | Red border | Passed
|  |  | TC_0020 | Peak button checking on 'Password' field | Peak button should allow the user to see the password. | Peak button worked accordingly. | abc123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the email address in 'Email Address' field 6) Enter a password in 'Password' field. |  | Peak | Passed
|  |  | TC_0021 | Password hide by masking. | Password should be masked so that the password is not shown publicly. | Shown as per expectations. | abc123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the email address in 'Email Address' field 6) Enter a password in 'Password' field. |  | Masking | Passed
|  |  | TC_0022 | Password' field with only alphabet | Validation message for only alphabet as password. | As per the expected results. | abcdef | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the valid email address in 'Email Address' field 6) Enter only alphabet in 'Password' field. |  | Only Letter | Passed
|  |  | TC_0023 | Password' field with only number | Validation message for only number as password. | As per the expected results. | 123456 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the valid email address in 'Email Address' field 6) Enter only number in 'Password' field. |  | Only Number | Passed
|  |  | TC_0024 | Space before password | Space before password should be accepted | Space was accepted as expected. | __abc123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the valid email address in 'Email Address' field 6) Enter space before password. |  | Space before password | Passed
|  |  | TC_0025 | Space in the middle of password | Space in the middle of password should be accepted. | Password accepted accordingly. | abc_123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the valid email address in 'Email Address' field 6) Enter space between the characters of password. |  | Middle space password | Passed
|  |  | TC_0026 | Space after password | Space after password should be accepted | Space was accepted as expected. | abc123__ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Click on 'Sign Up with Email' button 5) Enter the valid email address in 'Email Address' field 6) Enter space after password. |  | Space after password | Passed
|  |  | TC_0027 | Blank 'Full Name' field. | If any input is given in 'Full Name' field and all the data is erased then it will show a validation message. | It shows a validation message as expected. | Al Faysal Bin Asad, N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a name in 'Full Name' field then erase it |  | Blank_Full Name | Passed
|  |  | TC_0028 | Minimum character checking for 'Full Name' field | Less than minimum required character should not be accepted. | Didn't accept as per expectations. | A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter less than 2 character in 'Full Name' field. |  | Validation min char | Passed
|  |  | TC_0029 | Maximum character checking for 'Full Name' field | More than minimum required character should not be accepted. | Didn't accept as per expectations. | Al Faysal Bin Asad 1234567891234567891234567891238 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter more than 50 characters in 'Full Name' field. |  | Max char limit name | Passed
|  |  | TC_0030 | Space before name | Space should be allowed before Full Name. | It allowed accordingly. | ___________Al Faysal Bin Asad | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a name in 'Full Name' field with space before name. |  | Space before name | Passed
|  |  | TC_0031 | Space after name | Space should be allowed after Full Name. | It allowed accordingly. | Al Faysal Bin Asad________ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a name in 'Full Name' field with space after name. |  | Space after name | Passed
|  |  | TC_0032 | Valid name in 'Full Name' field. | A valid name should be accepted. | Accepted accordingly. | Al Faysal Bin Asad | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a name in 'Full Name' field. |  | Valid Full Name | Passed
|  |  | TC_0033 | Name with special character | Special character shouldn't be allowed with name. | Result was as per expectations. | Al Faysal Bin Asad@ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a name in 'Full Name' field with a special character. |  | Name with special char | Passed
|  |  | TC_0034 | Sign up with existing email | Already registered email shouldn't be allowed to register | Registered email was not allowed. | faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter an already registered mail. 5) Enter a valid password. 6) Enter a name in 'Full Name' field. 7) Click on 'Sign Up' button. |  | Sign up_registered email | Passed
|  |  | TC_0035 | Sign up without Gender and Birthday | Without entering 'Gender' and 'Birthday', 'Sign Up' will be possible. | Result was as per expectations. | faysalbinasad3334@yopmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a new email ID. 5) Enter a valid password. 6) Enter a name in 'Full Name' field. 7) Click on 'Sign Up' button. |  | Sign up without gender and birthday | Passed
|  |  | TC_0036 | Terms of Use' hyperlink checking during sign up with email. | After clicking 'Terms of Use' hyperlink, it will open a tab containing terms and conditions for the user. | Results was as per the expectations. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Terms of Use' hyperlink. |  | Terms_Email | Passed
|  |  | TC_0037 | Privacy Policy' hyperlink checking during sign up with email. | After clicking 'Privacy Policy' hyperlink, it will open a tab containing privacy policy for the user. | Results was as per the expectations. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Privacy Policy' hyperlink. |  | Privacy_Email | Passed
|  |  | TC_0038 | Offers and Promotions' checkbox checking | During sign up, by clicking on the checkbox, it will allow daraz to send mail regarding offers and promotions. | Worked as per the expectations. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a new email ID. 5) Enter a valid password. 6) Enter a name in 'Full Name' field. 7) Check the check box 'I'd like to receive exclusive offers and promotions via email' 8) Click on 'Sign Up' button. |  | Promotions_Email | Passed
|  |  | TC_0039 | Sign up with correct Email, Password and wrong Full Name | It shouldn't allow to sign up. | It didn't allow to sign up. | Email: faysalbinasad3334@yopmail.com Password: faysal1234 Full Name: Al Faysal Bin Asad@ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter a new email ID. 5) Enter a valid password. 6) Enter an invalid name in 'Full Name' field. 7) Click on 'Sign Up' button. |  | Email_Sign Up_Wrong Name | Passed
|  |  | TC_0040 | Sign up with correct Password and wrong Email, Full Name | It shouldn't allow to sign up. | It didn't allow to sign up. | Email: faysalbinasad3334@yopmail.com; Password: faysal1234 Full Name: Al Faysal Bin Asad@ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' 4) Enter an invalid new email ID. 5) Enter a valid password. 6) Enter an invalid name in 'Full Name' field. 7) Click on 'Sign Up' button. |  | Wrong Name and Mail Sign Up | Passed
|  |  | TC_0041 | Log in using Google+ | It should allow to Log in using a google account | It allowed to Log in accordingly. | Google Account: faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' Hyperlink. 4) Click on Google+ button 5) Select a Google+ account and allow to Log in. |  | Sign Up with Google+ | Passed
|  |  | TC_0042 | Log in using Facebook | It should allow to Log in using a Facebook account | It allowed to Log in accordingly. | A Facebook Account | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' Hyperlink. 4) Click on 'Facebook' Button 5) Select a Facebook+ account and allow to Log in. |  | Sign Up with Facebook | Passed
|  | Log In | TC_0043 | Sign In page appears or not | The Sign In page should appear by clicking on 'Sign Up / Login' button. | It appeared accordingly. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' |  | Sign In Page | Passed
|  |  | TC_0044 | Search Button checking | Search Button should work properly in Sign In page. | It worked properly. | Bag | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Write something in 'Search' box and click on 'Search' button. |  | Search Box_Sign In | Passed
|  |  | TC_0045 | Categories dropdown checking | Categories dropdown should display all of the categories after hovering over it. | It worked properly. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Hover over 'Categories'. |  | Categories_Sign Up | Passed
|  |  | TC_0046 | Add to Cart option checking | Add to Cart option shouldn't show anything before Login Sign In | It worked properly. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on Add to Cart logo. |  | Add to cart_Sign In | Passed
|  |  | TC_0047 | Register' hyperlink checking. | Register' hyper link should redirect to the 'SIGN UP' page for the new members. | It worked properly. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Register' hyperlink. |  | Register Hyperlink | Passed
|  |  | TC_0048 | Messages' button checking. | A new window will pop up after clicking on 'Messages' button but will not any show message before sign in. | It works as per the expectations. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Messages' button. |  | Messages_Sign In | Passed
|  |  | TC_0049 | Grammatical mistake in 'Sign In' page. | Verify whether there is any grammatical mistake or not. | No grammatical mistake found. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' |  | Grammatical Mistake_Sign In | Passed
|  |  | TC_0050 | Checking of alignment of the text boxes. | Alignment of text boxes should be accurate. | Found accurate. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' |  | Text Box Alignment | Passed
|  |  | TC_0051 | Log in using Google+ | It should allow to Log in using a google account | It allowed to Log in accordingly. | Google Account: faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on Google+ button 4) Select a Google+ account and allow to Log in. |  | Log in with Google+ | Passed
|  |  | TC_0052 | Log in using Facebook | It should allow to Log in using a Facebook account | It allowed to Log in accordingly. | A Facebook Account | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Facebook' Button 4) Select a Facebook+ account and allow to Log in. |  | Login with Facebook | Passed
|  |  | TC_0053 | Blank 'Email Address' field | Validation message will be shown for keeping 'Email Address' field blank. | Result shows as expected. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter an email address in 'Email Address' field then erase it. |  | Blank_Email_Sign In | Passed
|  |  | TC_0054 | Blank 'Email Address' and 'Password' field | Validation message will be shown for keeping 'Email Address' and 'Password' field blank. | Result shows as expected. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter an email address in 'Email Address' field then erase it. 4) Enter a password in 'Password' field then erase it. |  | Email and Pass Blank | Passed
|  |  | TC_0055 | Minimum character length checking of email. | Phone Number or Email' field will not accept the characters less than the minimum requirement and will show a validation message. | Didn't accept as per the expectations. | fay | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter character less than the minimum requirement in 'Phone Number or Email' field. |  | Minimum Email | Passed
|  |  | TC_0056 | Maximum character length checking of email. | Phone Number or Email' field will not accept the characters more than the maximum requirement and will show a validation message. | Accepted the characters though it exceeded the maximum limit. | faysalbinasad3334@gmail.com2345678912345678912345tyuiokj7854rfgjjbbg67895324fbjkmbhjkljfsfsdfrtreyrtur67547684736ertgrdgdfhtrutrujsaasteshgfjhgjuyiyuiyuiyuikyuiktuiyuikyuiyuigkghkfhkjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjjuyiuyi766666666666666666666666666666666666666666666666666666666666666666666666666khjjjjjjjjjjjjjjjjjjjjjjjjjjjjkjkudhfdgdfsdfsdffffffffffffffffffffvcbgnghmghkghkghkghkghkghkghkghkg | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter character more than the maximum requirement in 'Phone Number or Email' field. |  | Maximum Length Checking_Email | Failed
|  |  | TC_0057 | Character limit checking for 'Email or Phone Number' field within the range. | Phone Number or Email' field will accept the characters between the required character limit. | Accepted accordingly. | faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter character between the requirement in 'Phone Number and Email' field. |  | Between Limit_Email | Passed
|  |  | TC_0058 | Space before email address | Validation message for space before email address. | Didn't show any validation message. | _____faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter an email address in 'Phone Number or Email' field using space before email address. |  | Space Before Email | Failed
|  |  | TC_0059 | Space after email address | Validation message for space after email address. | Didn't show any validation message. | faysalbinasad3334@gmail.com_____ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter an email address in 'Phone Number or Email' field using space after email address. |  | Space After Email | Failed
|  |  | TC_0060 | Wrong Password checking. | A validation message will be shown for a wrong password. | Validation shown as per expectations. | Email: faysalbinasad3334@yopmail.com Pass: abc123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter a valid email address in 'Phone Number or Email' field. 4) Enter a wrong password in 'Password' field. |  | Error for Wrong Pass | Passed
|  |  | TC_0061 | Successful Login | Login will be successful with correct email address and password | Logged in successfully. | Email: faysalbinasad3334@yopmail.com Pass: faysal123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter a correct email address in 'Phone Number or Email' field. 4) Enter a correct password in 'Password' field. |  | Logged in | Passed
|  |  | TC_0062 | Login with wrong email and correct password | Login will not be successful with wrong email address and correct password | Didn't log in successfully. | Email: faysalbinasad@yopmail.com Pass: faysal123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter a wrong email address in 'Phone Number or Email' field. 4) Enter a correct password in 'Password' field. |  | Wrong Email, Correct Password | Passed
|  |  | TC_0063 | Login with wrong email and wrong password | Login will not be successful with wrong email address and wrong password | Didn't log in successfully. | Email: faysalbinasad@yopmail.com Pass: faysal1234 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter a wrong email address in 'Phone Number or Email' field. 4) Enter a wrong password in 'Password' field. |  | Login with wrong email and password | Passed
|  |  | TC_0064 | Phone Number or Email' field clear | Phone Number or Email' field should be cleared using a cross button. | It cleared successfully. | Email: faysalbinasad3334@yopmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter a email address in 'Phone Number or Email' field. 4) Clear 'Phone Number or Email' field using cross button. |  | Clear_Email | Passed
|  |  | TC_0065 | Asterisk sign for the mandatory fields | Asterisk signs should indicate the mandatory fields. | It works accordingly | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' |  | Asterisk Sign | Passed
|  |  | TC_0066 | 'Password' field clear | Password' field should be cleared using a cross button. | It cleared successfully. | Pass: faysal123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter a email address in 'Phone Number or Email' field. 4) Clear 'Password' field using cross button. |  | Clear Pass | Passed
|  |  | TC_0067 | Peak button checking on 'Password' field | Peak button should allow the user to see the password. | Peak button worked accordingly. | faysal123 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter a email address in 'Phone Number or Email' field. 4) Enter a password in 'Password' field. |  | Peak_Login | Passed
|  |  | TC_0068 | Password recovery checking using Email | Forgot Password?' hyperlink should redirect to another page to reset password. | Hyperlink worked as per the expectations. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. |  | Forgot Password | Passed
|  |  | TC_0069 | Returning to previous page from 'Forgot your password?' page. | Go back' hyperlink will allow to go back to the previous page. | It allowed accordingly. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Click on 'Go back' hyperlink. |  | Go back | Passed
|  |  | TC_0070 | Grammatical mistake in 'Forgot your password?' page. | No grammatical mistake will be found. | Didn't find any grammatical mistake. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. |  | Grammatical Mistake_Forgot | Passed
|  |  | TC_0071 | During resetting password, blank 'Email Address' field | Validation message will be shown for keeping 'Email Address' field blank. | Result shows as expected. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Email Address' field then erase it. |  | Blank Email_Forgot | Passed
|  |  | TC_0072 | During resetting password, minimum character length checking of email to reset password. | Phone Number or Email' field will not accept the characters less than the minimum requirement and will show a validation message. | Didn't accept as per the expectations. | fay | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter character less than the minimum requirement in 'Phone Number or Email' field. |  | Min Email_Forgot | Passed
|  |  | TC_0073 | During resetting password, character limit checking for 'Email or Phone Number' field within the range. | Phone Number or Email' field will accept the characters between the required character limit. | Accepted accordingly. | faysalbinasad3334@yopmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter character between the range in 'Phone Number or Email' field. |  | Correct mail_Forgot | Passed
|  |  | TC_0074 | During resetting password, maximum character length checking of email. | Phone Number or Email' field will not accept the characters more than the maximum requirement and will show a validation message. | Accepted the characters though it exceeded the maximum limit. | faysalbinasad3334@yopmail.com675674763gfhgfnvbhjjmkgfjhfj8hgjgjhfjdklnbjkgukgui766jhjllhljfkjfjjhxsgedty69hkjhkjgkfkbl;;;hugu8t865555555555jgkbkjbjkklhlh;j;oj;ojlhgiut8t56476ffiu | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter character more than the maximum requirement in 'Phone Number or Email' field. |  | No maximum limit | Passed
|  |  | TC_0075 | During resetting password, space before email address | Validation message for space before email address. | Didn't show any validation message. | _____faysalbinasad3334@yopmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field using space before email address. |  | Space Before Mail_Forgot Pass | Failed
|  |  | TC_0076 | During resetting password, space after email address | Validation message for space after email address. | Didn't show any validation message. | faysalbinasad3334@yopmail.com_____ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field using space after email address. |  | Space after mail_Forgot pass | Failed
|  |  | TC_0077 | During resetting password, 'Phone Number or Email' field clear | Phone Number or Email' field should be cleared using a cross button. | It cleared successfully. | Email: faysalbinasad3334@yopmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. |  | Clear Mail_Forgot Pass | Passed
|  |  | TC_0078 | To reset password, slide button checking to send OTP | After sliding the slide button to the right, a new page will be displayed containing confirmation button to verify the verification way (Email/SMS). | It worked accordingly. | Email: faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. |  | Slide Button_Forgot Pass | Passed
|  |  | TC_0079 | During password resetting, verification through Email. | After clicking on 'Verify through Email' button, it will redirect to another page named 'Email Verification' | It worked accordingly. | Email: faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button. |  | Verify Button_Forgot Password | Passed
|  |  | TC_0080 | In 'Email Verification' page, email address masking checking. | In 'Email Verification' page, email address will be masked. | Email address was masked. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button. |  | Masked Email | Passed
|  |  | TC_0081 | Alignment checking of the text boxes | Alignment should be accurate of the text boxes. | Alignment was accurate. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button. |  | Alignment of Text Boxes | Passed
|  |  | TC_0082 | To reset the password, 'Verification Code' receive via email. | A verification code will be received via email. | A verification code was received via email. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink.. |  | Verification Code | Passed
|  |  | TC_0083 | To reset password, timer checking to resend verification code. | A timer will be counted for 60 sec to resend the code again via email. | It worked accordingly. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. |  | Resend_Timer | Passed
|  |  | TC_0084 | To reset password, 'Resend' hyperlink expiry checking. | After a few minutes 'Resend' hyperlink will not send verification code. | It worked as per the expectations. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. |  | Token expired | Passed
|  |  | TC_0085 | To reset password, Re-entering of email address. | After refreshing 'Email Verification' page, re-entering of email address will be possible. | It was not possible accordingly. Email field was disabled. | faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Refresh 'Email Verification' page. |  | Re-write Email_Password | Failed
|  |  | TC_0086 | To reset password,resending verification code via email. | By clicking 'Resend' hyperlink, it will send a new verification code. | Code was sent again. | faysalbinasad3334@gmail.com | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. |  | Resend works | Passed
|  |  | TC_0087 | Email verification checking using code | After entering the verification code and after clicking on 'Verify Code' button it will be verified. | Code was verified accordingly. | Email: faysalbinasad3334@gmail.com Verification Code: 471654 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. |  | Verification Done | Passed
|  |  | TC_0088 | Asterisk sign checking in 'Rest Password' page. | New Password' and 'Retype' password field should be marked with asterisk sign since these are mandatory field. | Marked with asterisk sign. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. |  | Reset Password_Asterisk | Passed
|  |  | TC_0089 | Submit without new password. | Without providing new password 'Submit' button will not work. | Result was as per the expected result. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. 11) Click on 'Submit' button. |  | Submit without new pass | Passed
|  |  | TC_0090 | Alignment checking of the text boxes of 'Reset your password' boxes. | Alignment should be accurate of the text boxes. | Result was as per the expected result. | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. |  | Alignment_Submit | Passed
|  |  | TC_0091 | Peak button checking on 'New Password' and 'Retype Password' field | Peak button should allow the user to see the password. | Peak button worked accordingly. | 123456 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. 11) Enter a password and click on Peak Button. |  | Peak_Reset | Passed
|  |  | TC_0092 | Password hide by masking on 'New Password' and 'Retype Password' field. | Password should be masked so that the password is not shown publicly. | Shown as per expectations. | 123456 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. 11) Enter a password. |  | Masking_Reset | Passed
|  |  | TC_0093 | Message for containing password hints during setting new password. | When 'Password' field is blank it will show a hints to form a password | Password hints was shown as per the expectations | N/A | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. |  | Message_Reset | Passed
|  |  | TC_0094 | New password' field and 'Retype Password' clear during setting a new password. | By clicking on a cross button 'Password' field will be cleared. | Password' field was cleared as per the expectations. | 123456 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Click on 'Verify Code' button. 11) Enter a password. 12) Clear the password using cross button. |  | Clear reset pass | Passed
|  |  | TC_0095 | New password' field with only alphabet to set new password. | Validation message for only alphabet as password. | As per the expected results. | fahidabcd | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password with only alphabet. |  | Reset_Alphabet | Passed
|  |  | TC_0096 | New password' field with only number to set a new password. | Validation message for only number as password. | As per the expected results. | 123456 | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password with only alphabet |  | Only Number_Reset | Passed
|  |  | TC_0097 | New password' field with Alphabet, special character and number. | It should accept the new password characters with alphabet, number and special character. | As per the expected results. | faysal1234$ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password alphabet, number and special character. |  | Special Character_Reset | Passed
|  |  | TC_0098 | Space before password to set a new password. | Space before password should be accepted | Space was accepted as expected. | __faysal1234$ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password with a space before password. |  | Before Space_Reset Password | Passed
|  |  | TC_0099 | Space in the middle of password to set a new password. | Space in the middle of password should be accepted. | Password accepted accordingly. | fay__sal1234$ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password with a space middle of the password. |  | Space_Middle_Reset | Passed
|  |  | TC_0100 | Space after password to set a new password. | Space after password should be accepted | Space was accepted as expected. | faysal1234$__ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password with a space after the password. |  | Space_After_Reset | Passed
|  |  | TC_0101 | Retype Password' field validation checking for not matching password. | Validation message should be shown if the password of 'New password' and 'Retype Password' field don't match. | Validation shown accordingly. | faysal123$ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password in 'New Password' field. 11) Enter a different password in 'Retype Password' field other than 'New Password' field. |  | Password_Match | Passed
|  |  | TC_0102 | Retype Password' field validation checking for matching password. | Validation message should be shown if the password of 'New password' and 'Retype Password' field don't match. | Validation did not show accordingly. | faysal1234$ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password in 'New Password' field. 11) Enter the same password in 'Retype Password' field as like as 'New Password' field. |  | Validation for matched pass | Failed
|  |  | TC_0103 | Move to next field using keyboard. | From one text field to another text field will be possible using TAB button of the keyboard. | It worked accordingly. | faysal1234$ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password in 'New Password' field. 11) Press the 'TAB' button of the keyboard. |  | Move to next field | Passed
|  |  | TC_0104 | Password reset confirmation. | A confirmation message will be displayed for reseting the password. | It showed accordingly. | faysal1234$ | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Click on 'Forgot Password?' hyperlink. 4) Enter an email address in 'Phone Number or Email' field. 5) Slide the 'Slide' button to the right. 6) Click on the 'Verify through Email' button 7) Click on 'SEND' hyperlink. 8) Click on 'Resend' hyperlink. 9) Enter verification code. 10) Enter a new password in 'New Password' field. 11)Enter same password in 'Retype Password' field. 12) Click on 'Submit' button. |  | Confimration_Reset | Passed

## Bug Report
BUG REPORT
| Test Case ID | TC_056 | Test Case ID | TC_0058
| Module | User Management | Module | User Management
| Features | Log In | Features | Log In
| Issue | No validation for maximum character length of Email Address | Issue | Space before email address is accepted.
| Expected Result | Phone Number or Email' field will not accept the characters more than the maximum requirement and will show a validation message. | Expected Result | Validation message for space before email address.
| Actual Result | Accepted the characters though it exceeded the maximum limit. | Actual Result | Didn't show any validation message.
| Reproducing Steps | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter character less than the minimum requirement in 'Phone Number or Email' field. | Reproducing Steps | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter an email address in 'Phone Number or Email' field using space before email address.
| Environment | Production | Environment | Production
| Severity | Medium | Severity | Medium
| Bug Screen Shot | Maximum Length Checking_Email | Bug Screen Shot | Space Before Email
| Responsible QA | Al Faysal Bin Asad | Responsible QA | Al Faysal Bin Asad
| Test Case ID | TC_0059 | Test Case ID | TC_0075
| Module | User Management | Module | User Management
| Features | Log In | Features | Log In
| Issue | Space after email address is accepted. | Issue | During resetting password, space before email address is accepted.
| Expected Result | Validation message for space after email address. | Expected Result | Validation message for space before email address.
| Actual Result | Didn't show any validation message. | Actual Result | Didn't show any validation message.
| Reproducing Steps | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter an email address in 'Phone Number or Email' field using space after email address. | Reproducing Steps | 1) Go to https://www.daraz.com.bd/ using a browser 2) Click on 'SIGN UP/LOGIN' 3) Enter an email address in 'Phone Number or Email' field using space before email address.
| Environment | Production | Environment | Production
| Severity | Medium | Severity | Medium
| Bug Screen Shot | Space After Email | Bug Screen Shot | Space Before Mail_Forgot Pass
| Responsible QA | Al Faysal Bin Asad | Responsible QA | Al Faysal Bin Asad

## Test Metrics
Test Metrics
SL No. | Required Data | Data Count | SL No. | Test Metrics | Calculation | Result in Percentage
1 | No. of Requirements | 72
2 | Avg. No. of Test Cases Written Per Requirement | 52 | 1 | Percentage of Test Cases Executed | (No. of Test Cases Executed/Total No. of Test Cases Written) * 100 | 13
3 | Total No. of Test Cases Written for All Requirements | 800
4 | Total No. of Test Cases Executed | 104 | 2 | Percentage of Test Cases Not Executed | (No. of Test Cases Not Executed/Total No. of Test Cases Written) * 100 | 87
5 | No. of Test Cases 'Passed' | 97
6 | No. of Test Cases 'Failed' | 7 | 3 | Percentage of Test Cases Passed | (No. of Test Cases Passed/Total Test Cases Executed) * 100 | 93.2692
7 | No. of Test Cases 'Blocked' | 0
8 | No. of Test Cases 'Un Executed' | 696 | 4 | Percentage of Test Cases Failed | (No. of Test Cases Failed/Total Test Cases Executed) * 100 | 6.7308
9 | Total No. of Defects Identified | 7
10 | Critical Defects Count | 2 | 5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked/Total Test Cases Executed) * 100 | 0
11 | Higher Defects Count | 1
12 | Medium Defects Count | 2 | 6 | Defect Density: Number of defects identified per requirement/s | No. of defects found / Size (No. of requirements) | N/A
13 | Low Defects Count | 2
14 | Customer Defects | 3 | 7 | Defect Removal Efficiency (DRE): Fixed Defects : Defects identified during testing Missed Defects : Defects identified by the customer. | (Fixed defects / (Missed defects + Fixed Defects)) * 100 | N/A
15 | No. of Defects Found in UAT | 3
|  |  | 8 | Defect Leakage | (No. of defects found in UAT / No. of defects found in Testing) * 100 | N/A
|  |  | 9 | Defect Rejection Ratio | (No. of defects Rejected / No. of defects Raised) * 100 | N/A
|  |  | 10 | Defect Age | Fixed Date - Reported Date | N/A
|  |  | 11 | Customer Satisfaction | No. of complaints per period of time | N/A